Student Services Comprehensive Program Review: Timeline of Completion

| FIRST SEMESTER |  |  |
| --- | --- | --- |
| MONTH | TASK | PERSON RESPONSIBLE |
| February | ☐ Attend the Institutional Effectiveness Committee’s CPR Orientation. ☐ Arrange for a one-hour meeting in February/ early March with PRIE and all full-time faculty/ staff and relevant stakeholders about current evaluation practices and help needed. E-mail Becky Threewit with three meeting options. |  |
| February/ Early March | ☐ Meet with PRIE about current evaluation practices. Take inventory prior to the meeting and identify additional data needed. Request help with disaggregation if inputs include student IDs. Request additional data if needed by June. |  |
| March | ☐ Attend the IEC’s CPR work session on the Access and Effectiveness program data. |  |
|  | ☐ Attend the Curriculum Workshop co-hosted by the Curriculum Committee, forging a plan for the curricular updating. |  |
| April | ☐ Attend the current cohort’s CPR Share-Outs on the second Monday in April (Optional). |  |
| May | ☐ By May 1, meet with your dean to discuss your draft responses to the Access and Effectiveness sections of the CPR. |  |
| Summer | ☐ Enter and review PSLO and course SLO assessment results for the past year. Update CPR outcomes responses as needed. |  |
|  | ☐ Meet with PRIE to determine and plan for the student voice component if none exists. Surveys should be administered or focus groups conducted by the end of the fall semester (4.G). |  |

| SECOND SEMESTER |  |  |
| --- | --- | --- |
| MONTH | TASK | PERSON RESPONSIBLE |
| August | ☐ Continue updating course outlines of record (CoRs), per the Curriculum Committee’s submission schedule. |  |
| September | ☐ By September 25, meet with your dean to discuss your draft responses to the Background, Current Status and Key Findings sections of the CPR. |  |
| October | ☐ Attend the IEC’s CPR work session/ consultation. |  |
|  | ☐ By October 30, meet with your dean to discuss your draft responses to key findings, status updates for current goals and new goals-- including optional resource requests, and mapping of program goals to the Education Master Plan. |  |
| November | ☐ Attend the IEC’s work session/ consultation on program goals and how they emerged from the evaluation of your program’s effectiveness (Improvement Platform’s ‘Step 2: Goals and Resource Requests’). |  |
|  | ☐ Optional Resource Request: By November 15, submit the Annual Resource Request via the Improvement Platform’s ‘Step 2: Goals and Resource Requests.’ Work with your dean to complete the resource request and forge a plan to complete the forms needed for personnel and facilities requests if approved for funding. |  |

| THIRD SEMESTER |  |  |
| --- | --- | --- |
| MONTH | TASK | PERSON RESPONSIBLE |
| January | ☐ By January 29, submit the full CPR draft in the Nuventive Platform and meet with your dean to discuss it. |  |
| February | ☐ Consult with the IEC CPR Team for formative oral and written feedback on your CPR Draft, and revise as needed. |  |
| February/ March/ April | ☐ Create the CPR poster for the Share-Outs. |  |
| March/ April | ☐ On the Friday before spring break or by April 1, whichever comes first, submit the final CPR draft in the Nuventive Platform. |  |
| April | ☐ For the second Monday in April, designate a faculty/staff member to represent your program at the CPR Share Outs. Rally the team and invite colleagues to learn more about and support your program! |  |

Red- IEC Workshops/ Consultations

Bold- Due Dates/ Dean Consultations

Green- Student/ Learning Support Service Programs with Courses: Counseling, Educational Access Center, TRiO and the Learning Center.